## Sheet1
Date | Defect ID | Task ID | Defect Description | Defect Acceptance Criteria | RCA Analysis | AI BDD Generated Status | Task Done By
2025-04-10 | 45372 | 700356-1 | "slno shows wrong in mybank admin portal" | Serial numbers (Sl. No) in the MyBank admin portal must display in correct sequential order without any mismatch. | DataInconsistency | Yes | Vijayalaskhmi
2025-04-11 | 45293 | 700356-1 | "complaint report not showing in mybank admin portal" | Complaint reports must be visible and accessible in the MyBank admin portal. | DataFetch | Yes | Vijayalaskhmi
2025-04-15 | 45298 | 700356-1 | "export button not working in mybank" | Export button must work and allow successful download of complaint data. | Gap- Product knowledge (Functionality) | Yes | Vijayalaskhmi
2025-04-15 | 45299 | 700364-1 | "instead of month , showing account number in frequency field" | The Frequency field should display the corresponding month or frequency value (e.g., Monthly, Quarterly) instead of showing the account number. | Gap- Product knowledge (Mapping) | Yes | Vijayalaskhmi
2025-04-16 | 45339 | 700367-1 | "roi ,maturity amount and maturity date not loading automatically after entering amount" | ROI, Maturity Amount, and Maturity Date should auto-populate immediately after entering the amount. | Gap- Product knowledge (Coding Logical issue) | Yes | Vijayalaskhmi
2025-04-16 | 45341 | 700367-1 | "aadhar number field not showing in nominee page" | Aadhar number field should be visible on the nominee page. | Gap -Product knowledge( missing UI element) | Yes | Vijayalaskhmi
2025-04-17 | 45297 | 700373-1 | "content not possible to saw completely and alignment shows wrong" | News Content should be fully visible and properly aligned on both web and mobile platforms. | Responsiveness (Styling/Layout issue ) | Yes | Vijayalaskhmi
2025-04-17 | 45306 | 700375-1 | "app moving backward , instead of moving otp page ,page moving backward to interest page." | After proceeding, the app should navigate to the OTP page instead of returning to the interest page. | Gap - Product Knowledge (Navigation) | Yes | Vijayalaskhmi
2025-04-21 | 45333 | 700375-1 | "opened fd not showing in Term deposit Requests " | Opened fixed deposits should be displayed in the Term Deposit Requests section. | Gap -product knowledge (Data Synchronization) | Yes | Vijayalaskhmi
2025-04-21 | 45371 | 700375-1 | "term deposit request window not showing any data , after clicking on refresh button app keeps hanging" | After clicking the refresh button, the Term Deposit Request window should display updated data without causing the app to hang. | Product Knowledge | Yes | Vijayalaskhmi
2025-04-22 | 43090 | 650204-1 | "view button not showing in request status window against complaints" | The View button should be visible in the Request Status window for each complaint entry. | Product Knowledge | Yes | Vijayalaskhmi
2025-04-22 | 43115 | 650204-1 | "app keeps crashing while clicking on apk" | The app should not crash when clicking on the APK, and it should launch properly without any issues. | post-build validation not performed | Yes | Vijayalaskhmi
2025-04-23 | 43081 | 656152-1 | "no validation message shows up while adding own bank beneficary in other bank in eft window" | The system should display a validation message when adding an own bank beneficiary in the "Other Bank" section of the EFT window if no bank details are entered. | Missing validation logic in the backend | Yes | Vijayalaskhmi
2025-04-23 | 43166 | 670748-1 | While add news the notification is not showing as well from the floating menu News option selected and click on the news details app crashing. | The app should display news notifications correctly and navigate to the news details page without crashing when selecting the "News" option from the floating menu. | Backend failure or Server side Error handling | Yes | Vijayalaskhmi
2025-04-23 | 43165 | 674918-1 | While to TDS Exemption marking showing "Internal server error : 500" | The system should not return a 500 Internal Server Error when marking a TDS exemption | Unhandled backend exception | Yes | Vijayalaskhmi
2025-04-24 | 42887 | 664167-1 | "App keeps crashing while trying to log to application" | The application should not crash when the user attempts to log in. | App Crash | Yes | Vijayalaskhmi
2025-04-24 | 42903 | 664167-1 | "unknown error occurred " an popup shows up while opening loan opening window | The loan opening window should open without displaying an ""unknown error occurred" popup. | UnhandledException | Yes | Vijayalaskhmi
2025-04-24 | 43001 | 664167-1 | "ROI decimals shows more than 2 digits after decimal" | The ROI (Rate of Interest) should display a maximum of two decimal places after the decimal point. | Product Knowledge (Gap -Formatting ) | Yes | Vijayalaskhmi
2025-04-25 | 43202 | 664167-1 | "app redirects to homepage while selecting odkcc as product" | When the user selects "odkcc" as the product, the app should navigate to the corresponding product detail page instead of redirecting to the homepage. | Product Knowledge (Routing Configuration Issue) | Yes | Vijayalaskhmi
2025-04-25 | 43207 | 664167-1 | "currently drawing amount shows wrong against odkcc acc opening " | The system must display the correct drawing amount for the "odkcc" account opening based on the predefined calculation logic. | Product Knowledge(Data Mapping or Calculation Issue) | Yes | Vijayalaskhmi
2025-04-25 | 43227 | 664167-1 | "not possible to open odkcc account through mybank and also drwable amount shows wrong" | Users should be able to successfully open an ODKCC account through MyBank, and the drawable amount displayed must accurately reflect the correct available balance. | Product Knowledge (Intergation issue between Mybank and ODKCC account) | Yes | Vijayalaskhmi
2025-04-25 | 43239 | 664167-1 | "app got crashing while clicking on back button in summary page" | App should not crash when the back button is clicked on the summary page | NullPointer Exception | Yes | Vijayalaskhmi
2025-04-29 | 43041 | 656152-1 | "IFSC code not showing in eft outward table and also transfer type shows 1" | The EFT Outward table must display the correct IFSC code and show the transfer type in a readable format instead of a numeric value. | Data Mapping issue | Yes | Vijayalaskhmi